## Bug Reports
Bug ID | Title | Steps | Expected | Actual | Severity | Priority
BUG01 | Login button unresponsive | Click login | Login success | No action | Critical | High
BUG02 | No email validation | Enter wrong email | Show error | No error | High | High
BUG03 | Password visible | Type password | Masked | Visible | High | High
BUG04 | UI overlap mobile | Open mobile | Clean UI | Broken UI | Medium | Medium
BUG05 | Slow response | Click login | <2s | 10s delay | Low | Low
BUG06 | Duplicate request | Spam click login | 1 request | Multiple requests | High | Medium
BUG07 | Session not expired | Logout then back | Redirect login | Still logged in | Critical | High